## Phase I
Research Plan Schedule v1-29/06/2012
OKACOGNET
Dr. Jaine Gomez, Qiong Wu , Yujie Li, Xiaoyu Tang
Program start date
OKACOGNET:PHASE I
Researcher: Jaime
| Task | Start Date | End date | Weeks | Expected Outcome | Observations | Status
| T-PICA: Study Probabilistic ICA techniques for BOLD fMRI data analysis. | 22/06/2012 | 20/7/2012 | 4 | Theoretical understanding of the identification of ROIs with ICA-based techniques |  | Ongoing
| T-Net: graph analysis techniques for functional connectivity using Neuroinformatic databases. | 16/7/2012 | 2012-06-08 | 4 | Study network based tools for functional connectivity, assuming that the ROI are known (use neuroinformatic databases) | The connectivity matrix (the ROIs) are already given. | Scheduled
Researcher:Wu
| Task | Start Date | End date | Weeks | Outcome | Observations | Status
| T-PreSPM: Study of Preprocessing techniques using SPM for resting state experiment | [5 empty] | Completed
| T-DataAtt: Compile data from Attention experiments suitable to be used in functional connectivity networks | 27/06/2012 | 17/07/2012 | 3 | Obtention of ROI from fMRI voxels in attention experiment | Colaboration with Dr. Li | Ongoing
Researcher:Li
| Task | Start Date | End date | Weeks | Outcome | Observations | Status
| T-PreSPM: Study of Preprocessing techniques using SPM for resting state experiment | [5 empty] | Completed
| T-NewSoftware: Testing new software relevant for the project e.g. GIFT, AAL and others | [5 empty] | Ongoing
| T-GIFT: Use GIFT to obtain the components for the original experimental data set (24 healthy subjects in resting state condition) | 27/06/2012 | 17/07/2012 | 3 | Obtention of ICA components using ICA. Test different algorithms. Compare results with similar works on ICA-based study of funtional resting state | Work supervised by Jaime who will collaborate in the obtention of intermediate results | Ongoing
Researcher:Tang
| Task | Start Date | End date | Weeks | Outcome | Observations | Status
| T-LitEEG: Study of literature resting-state EEG functional connectivity | 2012-09-07 | 23/07/2012 | 2 | Understand the Synchronization likelihood (SL) parameter | http://www.ncbi.nlm.nih.gov/pubmed/20589941 | Scheduled